## Slide 1: Construction Project management
Prepared by:
Muath Saadeh
Saadeh Abu-Sa’da
Kamel Beshara

## Slide 2
Allar Municipality building
Graduating project consist two parts :
*The first part include preparing a theoretical research.
* The second part includes the application of the principle in construction project management.

## Slide 3
Contents
Project Time Management
Project Quality Management
Introduction
Project Scope Management
Project Cost Management

## Slide 4
Project Communications Management
6
Contents
Project Human Resource Management
7
Project Integration Management
8
Project Risk Management
9
Project Procurement Management
10

## Slide 5
What is Project?
* Project is the collection of activities, that are related or connected, for developing a product or a service,
* Projects have always start and end times.
* Projects have always a customer who uses the results.

## Slide 6
Cycle define project
unique
timescale
budget
Limited resources
Projects

## Slide 7
Define
Project
Management
What is Project Management?
Project Management is the skills, tools and management processes required to undertake a project successfully.
It is a set of principles, practices, and techniques applied to lead project teams and control project schedule, cost, and performance risks to result in delighted customers.
What is the Project Management Body of Knowledge (PMBOK)?
The Project Management Institute has identified nine topic areas to define the scope of project management knowledge as follows: scope, integration, time, cost, quality, human resources, communications, risk, and procurement.

## Slide 8
Brief Description Part Two
The building located in Allar village near Tulkarem city in the western strip of village
Allar municipality building is a 3 floor building consist of basement floor and 2 floors above the ground surface the basement contain a sport Jim and storage hall the ground floor (first floor ) contain a twelve storage rooms the second floor contain the employees offices and meeting and lecture hall
The area of the basement is 581.15m2 and the first floor area is 616.57m2 same as the second floor and the area the stairs and elevator section is 43.20m2 of the area of the land which the building is constructed in is 1290.00m2

## Slide 9
Drawings of Project:

## Slide 10
Allar Municipality Building
First will be planned for the project normally
and calculating the duration of the project and the total cost of project
The purpose of our study is to obtain the final cost, and duration for it.
In order to obtain these values we followed the following steps:

## Slide 11
Allar Municipality Building
1- Work breakdown structure:
The project is divided into activities in a process called work breakdown structure. In this project we breakdown in the following:

## Slide 12
Allar Municipality Building
2- Calculate the cost

## Slide 13
Allar Municipality Building
3-Schedual planning by primavera 6.0

## Slide 14
Allar Municipality Building
Total project cost = 2104555 NIS
Profit & Overhead 20% from total cost
The cost of structural work is = 1311071 NIS
The cost of mechanical work is = 95835 NIS
The cost of electrical work is = 82050 NIS
The cost of finishing work is =615600 NIS
Project start 04-Jul-2010 and end in 09-Jul-2011
Project duration 318 work day
Calendar 6day work in week
Results

## Slide 17
Update project
After the work schedule and start the implementation, we need to update the project data into compare the project actually and the planned project and the impact on the schedule.
Update date 10-4-2011

## Slide 18
Earned Value
CPI
EVA
SPI
Earned value
Update project
Earned value Reporting-Costs:
Earned value Reporting-Schedule:

## Slide 19
Earned Value
From this table we calculate the following:
Schedule Performance Index (SPI) =0.89
or
SPI=BCWP/BCWS=1497145/1674697=0..89 <1
SPI<1 behind Schedule (Project delayed)

## Slide 20
S-Curve
Update line 10-4-2011
PCWS (PV)
EAC
PCWP (EV)

## Slide 21
Muath , Saadeh , Kamel