An-Najah National University

Faculty Of Engineering

Civil Engineering Department

Construction Management Project

Graduation Project

Prepared by :

Mohammad Shehab                                         Khalid Mahmoud

Ahmad Mahajneh                                              Muataz Abd-Dayem

Supervision Dr:

Luay Dewikat

2011

Table Of Content.

PART ONE

CH 1                                 Introduction                                        Page

1.1   Definition of the project .                                                                    9

1.2   Definition of project management  .                                                  9

1.3   Objectives .                                                                                            10

1.4   Estimation .                                                                               	   10

1.5   Schedule definition .                                                                            11

1.6   work breakdown structure (WBS) .                                                   11

CH 2                                    Methodology.

2.1  Theoretical part .                                                                                   12

2.2  Practical part.                                                                                         13

CH 3                                    planning .

3.1  Introduction to Planning  .                                                                   15

3.1.1Relationship between scheduling and planning                             15

3.1.2 What should a typical plan contain.                                                15

3.1.3 Project control.                                                                                    15

3.1.4 Why schedule projects. 	16

3.1.5 Types of Knowledge that a schedule must have.                           16

CH 4                                    Scheduling the project.

4.1  Introduction.                                                                                      17

4.2  Estimating durations.                                                                    	 17

4.3  The critical path method.                                                     	  19

4.4  logic network .                                                                                  22

4.5  The CPM with computer software program.                               25

4.6  Definition Pertaining for the previous example .                        26

4.7   node format.       	      31

4.8  Lags             	       31

CH 5                                   Cost estimation.

5.1  Introduction.                                                                              	34

5.2  Uses of cost estimates.                                                                    34

5.3  Types of estimates.                                                                          36

5.4   Construction cost.	38

5.4.1   Direct cost.	39

5.4.1.1  Labor cost.	39

5.4.1.2  Material  cost .	 40

5.4.1.3  Equipment cost.	 41

5.4.2  Indirect cost .	 42

5.4.2.1  Overhead cost.	  42

5.4.2.2  profit                                                                                            42

5.5  Data required for preparing an estimate.	        43

5.6  Steps in  preparation of an estimate	        43

CH 6                                  Work breakdown structure.

6.1  Introduction.                                                                                  44

6.2  Definition of WBS.                                                                        44

6.3  Importance of breakdown structure.                                        45

6.4  Factors affecting WBS.                                                                 45

6.5  Steps to make WBS.                                                                     46

6.6  Example of WBS.                                                                          47

CH 7                                Project risk management

7.1 Overflow .                                                                                    49

7.2  Introduction.                                                   	49

7.3  Project risk management process.	51

7.4  When to use project management?	56

7.5  Planning a risk assessment 	57

7.6  Conclusion                                                                                  59

CH 8                               Quality management

8.1  Introduction.                                                                              61

8.2  Quality planning.	  61

8.2.1 Quality planning inputs                                                         62

8.3  Quality assurance .	   62

8.3.1  Quality assurance engineer.	   63

8.4  Quality control.	   63

8.4.1  Importance of quality control. 	   64

8.4.2  Quality control process.	   64

8.4.3 The test plane.	   64

8.5  Some issues to consider.                                                         65

PART TWO

APPLICATION OF CONSTRUCTION MANAGEMENT

((Al-Jadera Basic School))

Page

1-  Graduation project part two description

2-   Project description.                                                                                 	66

3 - Work Breakdown Structure(WBS).                                                                  68

4 – Quantity surveying.                                                                                            68

5 - Activities List and coding.                                                                                   68

6. Activity duration and productivity	69

7 - Bill of quantity (BOQ) preparation; quantities, cost, resources,

and man hours.                          	69

8 – Project price .                                                    	70

9- Project network.                                                        	70

10 –Project budgeted.                                                                                              70

11 –Project duration.                                                                                              70

12-  Result & Conclusion

APPENDIX

Appendix A:   Work Breakdown Structure(WBS)

Appendix B:   Quantity surveying

Appendix C:    Activities List and coding

Appendix D:   Bill of quantity (BOQ) preparation; quantities, cost, resources, and man hours

Appendix E:     Project price

Appendix F:     Project network

Appendix G:    Project budgeted

Appendix H:    Project duration

الإهداء

إلى السنبلة الذهبيّة في بِلادي و بيّارات البرتقال 
إلى كرومِ العِنَب و غصن الزيتون و دَم الشهداء و دَمعة الأطفال 
إلى رغيف الطابون و ريح الزَعتر 
إلى فِلسطين تِلك التي صَنعتني كَي أكونَ هُنا 
إلى مَن علّمني كَيف الصعود و حَمل لي شُعلةً
تلذذ بحروقاتِها في يَديهِ لينيرَ لي دَربي 
إلى ذاك الرَجل الذي عَلَمني العِزّة و كحّل عينيّ بالكِبرياء
إلى ذاكَ الذي ما زالَت عينيه تَصنعني طِفلاً حَتّى اللحظة .!
" إليكَ والدي "
و إليها ..
و إلى الحضن المعبَق بأريج الوَطن 
و اليَد التي اندّست في خِصال شِعري و صوتها الشجيّ يَروي لي حَكايا الجِدّ و النجاح قَبل النوم كَي أحلُم بِها 
مَن علّمتني كَيف أقِف أمامَكم في لَحظةٍ تَتسابق فيها الدموع لمقلتيّ 
" إليكِ أمّي "
و لكلّ مَن صنعوني مَعكما و حفّتني و إياهم ذِكريات بيتٍ واحِد 
إلى مَن اجتمعوا مَعي على دِفء مَوقِد الشِتاء و تَقاسموا مَعي ظلمَة ليلِ واحِدة 
" إليكم إخوتي "

و لا أنسى مَن علّمني حَرفاً أن أكونَ له  عَبداً
و كلّ مَن سَبقني الطَريق و سيلحَقني إليها مِن طلاّب عِلم 
لِجامعتي التي تركتُ مذكّراتي عَلى مقاعِدها 
لكم جَميعا أُهدي سَهري و تَعبي و جَهدي

شكر وتقدير

بسم الله الرحمن الرحيم

( وقل اعملوا فسيرى الله عملكم ورسوله والمؤمنون ) . صدق الله العظيم

أتشرف في بداية مشروع التخرج هذا والذي آمل أن ينال إعجابكم وتقديركم أن أتقدم بالشكر الجزيل إلى الأستاذ الكريم لؤي دويكات الذي بذل جهداً منقطع النظير في تقديم التوجيه والإرشاد ليكون هذا العمل في المستوى المطلوب علماً بأنني اعترف بتقصيري في الشكر لأن ما قام به هو اكبر من الشكر والتقدير لكنّه الأب الذي لا ينتظر من أبنائه شكراً والأستاذ الذي تغمره الفرحة بنجاح طلابه ليكونوا عماد هذه الأمة وسندها في معارج الرقي والتقدم هذا

وشكري موصول إلا الأستاذ الطيب المعطاء إبراهيم محاميد الذي سايرني في مراحل المشروع الأولى فالشكر الجزيل لكم جميعاً أساتذتي أعضاء الهيئة التدريسية الشرفاء في جامعتنا العريقة جامعة النجاح الوطنية .

PART ONE:                 Chapter 1:

Introduction:

Project management in the modern sense began in the early 1960’s, the need for project management was developed by businesses who released the benefits of managing work. So project management is not a new fad, it is a professional task that has wide acceptance in industries from government to technology. management of construction projects include a three steps process that require the involvement of all parties on work site, Each step requires the commitment and dedication of all project team members, all are essential to the successful outcome of a construction project, and to long term success of a construction firm.

- Definitions:

1.1 Definition of project:

A project is a temporary with starting time activity which has specific goals and conditions, defined responsibilities, a budgeted, a planning, a fixed end date and multiple parties involved.

1.2 Definition of project management:

Project management is the discipline of managing all the project resources and aspects in a manner leads to deliver all the outputs which is required to complete the project within a defined time, scope, cost and efforts.

We have three major project management tasks for the project manager:

- Setting goals: to determine the goals of the project and what is the project is aim to.

- Creating a project management system.

We have to focus on these three elements:

- Time; to insure the work is done in the correct order. For any project there should be a start and finish time.

- Cost; the work must be performed efficiently. Cost estimation for the project should be performed and studying the final benefits of this project.

- Resources; determine when and how much of resources. The availability of these resources and its influence in total cost and time duration of the project.

- Finances; financial control means accurately predicting the amount of each needed to support work done on the job.

- Managing the project:

- Plane; usable schedules and budgets must be established for all phases of the job.

- Communication; the plans must be communicated clearly and effectively to the people who will be executing them.

- Monitor and control; after the planes have been developed and communicated, they must be carried out by project personnel.

Project management is often summarized as a triangle. Time, cost and scope which are the main factors affecting the project management are put in vertices with quality as a central them.

  - Objectives:

- To study the project from an engineering view.

- Put a compatible planning for doing project.

- Provide a suitable estimation for the project.

- Provide the needed schedules for the project.

  - Estimation:

Estimation is a calculated approximation for results even if these results are incomplete or uncertain.

Project estimation includes an approximation of needed quantities, an approximation of how long it would take, and an approximation how much it would cost.

  - Schedule definition:

In general schedule is time planning. In project management schedule is a list of work elements with specific time for start and end each element.

According to “Wikipedia” A timetable or schedule’ is an organized list, usually set out in tabular form, providing information about a series of arranged events: in particular, the time at which it is planned these events will take place.’

Scheduling is then a five-step process:

- Identify the time you have available.

- Block in the essential tasks you must carry out to succeed in your job.

- Schedule in high priority urgent tasks and vital "house-keeping" activities.

- Block in appropriate contingency time to handle unpredictable interruptions.

- In the time that remains, schedule the activities that address your priorities and personal goals.

  - Work Breakdown Structure (WBS):

WBS is a serial description of all activities to design a project, it is a stage in classic project management methodology where the project development is divided into stages showing time and sources needed to complete each stage of development, project discrete comes in a manner which helps organize and define each work stage of the project.

A sample WBS is shown in the figure below:

WBS Format for System Development Projects

Chapter 2:

Methodology

This research will introduce an example of project managing.  research will include 2 parts:  theoretical one and practical one.

2.1. Theoretical part includes the following chapters:

- Planning and Scheduling: it’s the process by which you look to the time that is available to you, and plan it in a way that will satisfy your goals. It can be defined as the processes of breaking the project down into workable sub – parts, or activities, and then determining the sequence of work that will be used to accomplish those activities.

Scheduling “time management refers to all skills, techniques and tools that are used to manage time, one goal of time management is to help in making aware of how to use the time as source of organizing, planning and succeeding of the project.

- Cost management: cost management is one of the basic fundamentals of the project management. It helps you to make sure that only expenses which are approved are taking place, it also help you to keep your project plan up to date with the latest expenses available. Cost estimating is the process of analyzing a specific scope of the work and predicting the cost of performing the work. Cost estimating involves collecting, analyzing, and summarizing all available data pertaining to a project.

- Work break down structure: it is a process by which the main project is break down into smaller activities in order to make it easier to dial with each activity and managing it, it can also be a tabular list of "element" categories and tasks or the indented task list that appears in your chart schedule.

- Resource management: one of the most important part of project management is the source management. It is the efficient and effective deployment for an organization's resources when they are needed. Such resources may include financial resources, inventory, human skills, production resources, or information technology …

- Risk management: Risk is an entity that appears in all aspects of projects. The purpose of project risk management is to improve project performance by systematically identifying and assessing risks, developing strategies to reduce or avoid them and maximizing opportunities.

- Quality control; it is a process employed to insure a certain level of quality in a certain project, quality control involves the examination of a product, service, or process for certain minimum levels of quality. The goal of a quality control team is to identify products or services that do not meet a company’s specified standards of quality.

2.2. Practical part will be accomplished by hand calculations for the estimation and using software like primavera for scheduling and time duration. It includes the following chapters:

- Quality surveying:  this chapter will show the surveying data and calculations. And using the results to manage the work quality and control cost and time.

- Cost estimation:  determining the material needed; number of working people; any other requirement to finish the project; we can estimate the total cost of the project. This process will illustrate in this chapter.

- Resource management: taking in consideration what we will need and what is the benefits and when we will receive it we can control the resources to make balance between incomes and outcomes. This calculation will appear in this chapter.

- Scheduling: after calculate total cost and control resources a time table could be put which will show each activity; it’s duration; starting time and finishing time. We will put this time table in this chapter.

- Total duration: calculations of total time that will be needed to complete the project this will come as a result of scheduling and the time estimating taking in consideration any time obstacles that me be appear.

Chapter 3:

Planning

3.1 Introduction to Planning

The term planning is used in many ways and different contexts. We commonly here about financial planning, such as retirement planning and college education planning Although this type of planning may include other aspects (such as what to do after retirement or which college to choose for your child ), the main focus is on finance but in our study we mean the term planning is restricted to meaning project planning , with an emphasis on construction project .

Project planning has been defined as the process of choosing the one method and order of work to be a doped for a project from all the various ways and sequences in which it could be done.

3.1.1 Relationship between scheduling and planning

Project planning answer the questions What is going to be done? How? Where? By whom? And When?(in general terms , the project's start and end )? , scheduling deals with When on a detailed level

3.1.2 What should a typical plan contain:

-  A scope definition, such as a five –story building for commercial use (offices) with a total area of about 30,000 square feet.

-  A schematic design. This is not a must but helps you visualize the project. The final design may later differ significantly

-  A budget number. The planner must be aware of all construction –related expenses

-  A time frame (when the project is expected to start and end)

-  Other pertinent information that may be used to justify the project or clarify some of its aspects

3.1.3 Project control

It's of utmost importance to know – at all times – where you stand in relation to where you planned to be (the baseline) . if you find yourself behind schedule or over budget, you must know why , then take corrective action to get back on track, or at least minimize the deviation, this process exemplifies  project control .

3.1.4 Why schedule projects

* To calculate the project completion date.

* To calculate the start or end of specific activity.

* To expose and adjust conflicts between trades or subcontractor.

* To predict and calculate the cash flow.

* To evaluate the effect of changes " changing orders"

* To improve work efficiency by properly distributed workers and equipment

* To resolve delay claims , construction delay claim are common lawyers often use expert witnesses who are professional scheduler , in most cases ,only the critical path method schedule can prove or disprove a delay claim .

* To serve as an effective project control tool

3.1.5 Types of Knowledge that a schedule must have .

*Knowledge of computer software and hardware

* Knowledge of principles of scheduling and project control (as part of project management)

* Knowledge of the specific technical filed, such as commercial building , industrial, transportation

Chapter 4

Scheduling the project

4.1   Introduction:

The processes of breaking the project down into workable sub – parts, or activities, and then determining the sequence of work that will be used to accomplish those activities.

Once these two tasks are complete, the project manager has carried some tools to help finish the job, however since no time information has yet been developed. This chapter addresses time issues:

1. Estimating the time of individual activities, and

2. Calculating the length of the job as a hole.

4.2   Estimating durations:

Some general rules should be noted

* Assume each activity will be done normally

The reason for using this assumption can be seen in the following figure which relates efficiency ,or unit cost ,to activity time

* Evaluate each activity independently

The scheduler should evaluate each activity times as no other work existed

* Use consistent time units

The time used to describe activity and project durations are work days .These work days are converted to calendar days through the calendar definition process ,although hours or weeks can be used .

It is important to be constant to prevent confusion and misunderstanding over the scheduled times for various type of job

* Keep Good records as the schedule is developed

It is often helpful during the schedule development process to be able to refer to previous assumptions ,calculations .

It is essential that construction companies maintain and use good scheduling systems so that projects can be kept on track and can be completed on time.

4.3   The critical path method

Of all the techniques available to project manager ,CPM has proven the most useful and effective means of developing and displaying the information needed to control the time variables on today's job sites

For example ,in building a house  both foundation and stud wall are essential elements . The crew that forms and places the foundation is very different from the one that erect and stud the walls.

Nevertheless ,these tasks are independent in that the walls can not begin until the foundation is complete .

Example for CPM is hunting describe in the following  figure

Figure 4.1

1.5 The basic steps for scheduling are as follows

* Determining the work activities: for any project no matter how large or small ,must be divided into smaller entities, called activities

We have two schools of thought:

**Restrict the number of activities for the simplicity of the project schedule

**Break the project down into small activities this approach will result in large number of activities ,the main advantage of is better to control of  the schedule during execution

**One way to break down aproject is by using WBS

* Determining activity duration :

Most activity duration can estimate as follow:

For example :

For 10000 CY "cubic yard" the excavation and a crew that avarege 800 CY per day

Duration = 10000 / 800 = 12.5day

This information could come from the project team (project manager , project superintendent ) , how receives feedback from field crew leader or from subcontractor.

* Determine a logical relationship:

The schedule should obtain the information from project manager and technical team leader , which should not be confused by constrains:

** A logical relationship exist between two activities when the start of one activity or finish ,for example you cannot place the concrete until finish the frame work and reinforcement

**A resource constrain or restriction : is theoretically you can do task in the same time with the availability of material and labor for just one task of these

* Draw a logic network ,and perform the critical path calculations.

* Review and analyze  the schedule : you have make sure there is no redundant relationship

Some common errors:

** Wrong relationship is when the relationship is connected to the wrong activity or with the appropriate activity but at wrong end  (eg , you connect the end of the activity when the relation is start to start)

** Missing relationship :when the predecessor of an activity is simply not shown

** Redundant relationship : when ,for example ,C requires B and B requires A ,if you draw A and B as predecessor of C ,A is redundant predecessor of C

** A logic loop :when you leave a point in the network ,then return to it later (eg , A requires B ,but B requires A) as shown in the figure "b" above.

* Implement the schedule: means taking the schedule from paper to execution , three important point should be considered.

** The schedule must be realistic and Fairley accurate.

**The paper manager must take it seriously.

**Such implementation and commitment must continue throughout the project.

* Monitoring and control the schedule : means compare the baseline what was planned or what was supposed to be done with what has actually been done ,and taking corrective action whenever or wherever needed .

* Revise the data base and record  feedback: this process is continues and iterative , all costs and time estimate are based on past experience ,this past experience must be documented in a well – organized easy – to -  retrieve fashion.

* Implement resource allocation and leveling: means assign the correct amount for each activity  , for leveling means trying to maintain uniform daily use of a resource for the entire live cycle of the project , the objective of this step :

** To link scheduling with estimating and accounting , at any point in the project you should be able to tell the total budget.

**To improve the efficiency of the resources ( particlary labor and equipment) used by the process of leveling.

4.4   Logic network

can explain by the following example:

Example (1):

In this example we need to calculate  two type of dates:

* The expected completion date of project.

* The earliest dates when each activity can start or finish.

These dates are called the early start (ES) or the early finish (EF) dates of each activity.

In mathematical teams ,the early start time of activity are as follow

The Forward pass

Where the (EFi) represent the early finish times of all preceding activities.

Likewise the (EF) time for activity j are as follow:

Where (DURj) ,duration of activity j.

The forward pass is defined as the process of navigating through a network from start to finish and calculating the early dates for each activity and the completion date of the project .

The Backward pass:

In mathematical terms the late finish time (LF) for activity j are as follow:

Where (LSk) represent the late start times for all the succeeding activities.

Likewise , the late start (LS) time for activity j (LSj) is as follow:

the backward pass is defined as the process of navigating through a network from finish to start and calculating the late dates for all activities.

This pass , along with the forward pass calculation  ,help to identify the critical bath and the float for all activities  .

There are several type of float . the simplest and most important type of float is Total Float (TF)

If we tabulate the result we got the following table:

With the Backward Pass, we have calculated tow type of data.

* The late dates for all activities, which indicate the critical path.

* The amount of float for each non critical activity.

Following are six observations about the critical path:

* In every network, at least one critical path must be exist.

* More than one critical path may exist; multiple paths may share some activities.

* Any critical path must be continues from start of the project to it is end.

* Unless constrain is imposed, path cannot be partially critical   .The entire path must be either critical or non critical.

* If all paths in a network must go through one particular activity, this activity must be critical

* Critical path can be defined as the longest path in a network

5.5    The CPM with computer software program:

If we plot the previous CPM network by using one of the commercially available software program ,such as primavera project planner or Microsoft (MS) project  the following figure will show the process.

This process will affect the forward pass and the backward pass as the following:

The only difference between these network and these software is the start dates because these computer software use the start of the day when calculating start dates ,and the end of the dates when calculating finish dates ,this approach affect the forward pass and the backward pass calculations.

4.6     Definition pertaining for the previous example :

* Activity ,or task : a basic unit of work as a part of the total project that is easily measured and controlled . It is time and resource consuming

* Backward pass : the process of navigating through a network from end to start and calculating the late dates for each activity

* Critical path : the longest path in a network from start to finish

* Critical activity : an activity on the critical path, any delay in the start or finish of a critical activity will result in delay in the entire project

* Early dates : the early start date and the early finish date of an activity.

* Early finish (EF) : the earliest dates in which an activity can finish without violating the logic.

* Early start (ES) : the earliest dates in which an activity can start without violating the log * Event : a point in time marking a start or an end of an activity .

* Forward pass : the process of navigating through a network from start to end and calculating the finish date for the entire project and the early dates for each activity.

* Backward pass : is the opposite of the forward pass.

* Late dates : the late start date and the late finish date for an activity.

* Late finish (LF): the latest date on which an activity can finish without extending the project duration.

* Late start (LS) : the earliest date on which an activity can start without extending the project duration.

* Total float (TF): the maximum amount of time an activity can be delayed from it is early start without delaying the entire project.

Example that show the forward  ,backward and total float calculations

Example(2):

Solution:

Performing forward and backward passes yields the solution shown in the above figure . The critical path is A ,C ,F ,H ,I  . Activities B ,D ,E and G have total floats equal to  2, 13 ,2 and 7 respectively

Free Float (FF):

The maximum amount of time an activity can be delayed without delaying the early start of the succeeding activities.

We must always realize that  FF is less than or equal TF . In the FF is the part of total float that will not affect the early start of the following activities .

To calculate free float ,we need to compare the activity's early finish dates with its successor's early start date . When there is one successor activity the calculation is simple  as shown in the following figure.

Figure 1.4

Activity G's FF = 22 – 15 =7 days

When the activity has more than one successor activity , we must pick the earliest early start date among the successors.

Figure 1.5

Activity B's FF = min(8,12) – 8 = 0

In general the FF is calculated using the following equation:

The other parts, interfering float ,may be defined as the maximum amount of time an activity can be delayed without delaying the entire project but causing delay to the succeeding activities . It represents the part of the total float that remains after free float is deducted :

OR

If we look at the Independent float  ( Ind – F) for an activity , which is not shared or affected by any other activity , we may define it as the maximum amount of time an activity can be delayed without delaying the early start of the succeeding activities and without being affected by the allowable delay of the preceding activities Can be calculated as follow :

An example for performing the CPM computations for the schedule shown below :

Example (3)

Performing forward and backward calculations will result the following network

Performing the CPM calculations ,we find the early dates ,the late dates ,total float ,and the free float for all activities ,as shown in the following table :

Calculations for total float and free float are shown in the table above , an example for calculating independent  float as follow :

Ind – F for activity E = 22  -15 – 6 =1 day

The result could be negative , which could be interpreted  as zero independent float ,so make sure that end .F is less than or equal FF .

Interfering float and independent float are not used in construction scheduling or even calculated by commercially available software scheduling programs , they are sometimes used  ,although rarely  , in delay – claims resolution.

4.7   Node format

Figure 4.2

4.8   Lags :

A lag is a mandatory waiting period between the completion (or start) of an activity and the start (or completion )of its successor , and a lead is a negative lag . Although lags are not real activities ,they consume time and must be incorporated into the CPM calculations . They are shown as numbers above the of arrows .

Redo the previous example ,

Performing forward and backward passes yields to the solution shown in the following figure

The 4 days lag between activity A and D means that activity D cannot start until 4 days after the completion of activity A .The same principle applied to the lags between activities B and F and between the activities H and I .

Chapter (5)

Cost estimation

5.1    Introduction:

Cost estimating is the process of analyzing a specific scope of work and predicting the cost of performing the work. The accuracy of the estimate is a function of how well the specific scope of work is defined and the time available to the estimator. The basic challenges the construction contractor faces are to estimate the costs of constructing a project, schedule the specific construction activities, and then build the project within the estimated cost and schedule. Therefore, cost estimating and cost control skills are essential if the construction contractor is to build a project profitably.

Cost estimating involves collecting, analyzing, and summarizing all available data pertaining to a project. The data may consist of a rough concept of the gross area or volume of a project, or it may be a set of detailed plans and specifications. Using whatever data is available; the estimator first divides the project into components or elements of work and then estimates the cost for each of these. The estimate may be based on an estimated gross cost per component or element of work, or it may be based on individual labor, material, equipment, or subcontractor estimated costs for each. The estimated cost for the project is then determined by adding the estimated costs for all of the components or elements of work.

5.2       USES OF COST ESTIMATES:

The project designer needs to have updated cost estimates throughout the design process to ensure that the project  is being designed in Such a manner that it can he constructed within the owner's budget The construction contractor must be able to forecast the construction cost to prepare a hid or negotiate a contract price to win the project and to estimate the cost impacts of change orders during the execution of the project.

Some of the primary uses of cost estimates in construction are as follows:

•Developing an initial project budget for an owner. An initial budget estimate is usually prepared during the programming phase. It may he prepared by the design firm, a consultant, or the construction contractor to estimate project funding requirements. This budget may he used by the owner to obtain financing for the project. Financing for the project.

•Determining project feasibility. A cost estimate may he prepared for a project owner to determine whether or not the project is affordable or whether or not anticipated revenues Would justify the investment in constructing the project.

•Designing the project within the owner's budget. Cost estimates may be prepared at various milestones during the design process to ensure that the estimated cost of construction is within the budget established by the owner.

•Evaluating alternative design concepts and project components. The design team may he considering alternative building Systems or components. Cost estimates for each system Or component under consideration usually are prepared to assess the cost impacts of the alternatives being considered.

•Preparing bids. Cost estimates are prepared by construction contractors to determine their bid amounts for a bid procurement process.

•Preparing cost proposals. Cost estimates are prepared by construction contractors to justify their cost proposals in a negotiated procurement process.

•Establishing project ject budgets. Construction contractors often use their updated cost estimates to establish their project budgets once they are awarded a construction contract.

•Determining cost impacts of change orders (CO). Contract change orders modify the scope of work. The construction contractor prepares a cost estimate to predict the cost impacts of the scope modifications. These estimates are used by the contractor to negotiate an adjustment to the contract value as compensation for the additional work.

•Substantiating claims and resolving disputes. Construction contractors may perceive that they incurred additional work because of a differing site condition or some problem with the design documents. Consequently they may wish to submit claims for additional compensation for the cost of the additional work. Cost estimates would be prepared to support the contractors' claims. These estimates also may be used by mediators or arbitrators in resolving disputes that may result from unresolved claims.

•Preparing a schedule of values used to justify progress payment requests. A schedule of values is a breakdown of the contract value that shows the estimated cost of the major project components. It is prepared from the contractor's cost estimate for the project. The schedule of values is used to justify the progress payment requests on lump-sum contracts.

•Creating historical cost databases. Actual cost data may be collected to create an as-built estimate used to update a cost estimating database that can be used in estimating future projects.

#### 5.3      TYPES OF COST ESTIMATES:

There are three major types of cost estimates. Conceptual cost estimates are developed using incomplete project documentation; for example, during programming and schematic design. Semi-detailed cost estimates are prepared when parts of the project have been completely designed, while other aspects have not; for example, during design development. Detailed cost estimates are prepared based on fully developed construction drawings and specifications. There is no single estimate for any project.

There are good estimates, and there are bad estimates. Cost estimating is as much a learned skill as it is a science. Estimating material costs generally is not difficult, as it involves measuring the scope of work from the contract drawings. Estimating labor and equipment costs, however, requires knowledge of construction techniques and experienced judgment. The greatest uncertainty is in predicting the productivity of the crews and equipment that will be used on the project.  This will vary based on job conditions, crew size, crew experience, and equipment selected. The accuracy of the estimate will depend upon the completeness of the contract documents and the experience of the estimator. The typical accuracy of the various types of cost estimates is shown in Figure 1-2.

- Conceptual Cost Estimates

A conceptual cost estimate is a quick method for determining an approximate cost of a project without benefit of a detailed definition of the exact scope of work. Three types of conceptual cost estimates are used in the construction industry. They are:

- rough-order-of- magnitude (ROM) cost estimates: When a project is started and Requirements are not specified in great detail, the exact project Budget can not be calculated without mistakes (due to the well-known Cone of Uncertainty). Concrete numbers in this stage will lead to an ineffective situation in which you or us may experience loss.

- assemblies cost estimates:

A faster and more cost-effective method is needed for the planning phase of a building project.  An Assemblies Estimate is usually prepared when the architect completes the design development plans. The assemblies method is a logical, sequential approach which reflects how a building is constructed.

- cost indices:

is an indicator of the average cost movement over time of a fixed basket of representative goods and services related to Construction Industry.

Type of Estimate Construction Document Development; Expected Percent Error*.

Conceptual Semi-Detailed Detailed; Schematic Design 0-30% Construction Documents Design Development 30-90% Construction Documents 90-100% Plans and Specifications.

*Percent error means the expected variation between the cost estimate and the actual cost

Table 5-1  Accuracy of different types of cost estimates.

- Semi-Detailed Cost Estimates

Semi-detailed cost estimates are developed while basic design decisions are being made to verify that the project can he constructed at its intended scope within the owner's budget. Some aspects of the project may be completely designed -the foundations for example- while some of the architectural features are yet to be determined. Detailed estimating methods can be used to estimate the cost of project components that have been designed, and Conceptual estimating methods are used to estimate the cost of those components that remain to be designed. This means that databases are used to estimate the cost of components for which the design is not complete, and project data are used to estimate the cost of components for which the design is complete. Therefore, these estimates are known as semi-detailed cost estimates

- Detailed Cost Estimates

Detailed cost estimates are prepared once the design has been completed and all construction documents prepared. The estimator divides the project into individual elements of work and estimates the quantities of work for each element. Dividing the project

#### Scope into elements of work is known as the work breakdown, and estimating the individual quantities of work is known as the quantity take - off (QTO). Next the individual elements of work are priced to determine an estimated cost for each one. The estimated costs are summed, and overhead costs are added to cover the contractor's cost of managing the work. The estimated costs of constricting the project are known as the direct costs, and the overhead costs are known as the indirect costs. Two Formats are commonly used in developing detailed cost estimates :

- a systems format, known as the Uniformat.

#### It is organized by building components or systems .

- the Master format.

#### It is organized similar to the technical specifications used in most construction              contracts.

#### 5.4      construction cost:

#### The rate per unit of any item of works , depends upon the cost of material , cost of labor , and other miscellaneous expenses , such as sundries , contractor's profit and overhead expenditures .

- Cost: The cost directly attributable to an element of work, including direct overheads

- price: The cost of an element of work, plus allowance for general overheads, insurance, taxes, finance (i.e. interest charge) and profit (sometimes known as 'contribution') which is charged for executing the work

A sub-contractor’s price , including profit, etc. is a cost to a main contractor.

5.4.1           direct Cost:

Direct cost contains:

- Labor cost.

- Material cost.

- Equipment or plant cost

#### 5.4.1.1        Labor Cost:

#### General contracting  is a challenge because a contractor bids to perform work for the lowest price with a temporary workforce. The key to being effective is to have key field personal that can direct and perform to work efficiently and correctly. Direct labor is a general contractor's own labor force that does construction work.

#### It also represents his or her firm's greatest risk. Labor cost is determined in one of several ways. An estimator must be aware of these methods, because some bids may ask for labor  rates, and he or she must know the proper way to determine them. Some of the factors of labor pricing as follows:

- Productivity Factors vs. Labor Unit Prices

Labor cost can be determine by using in either labor unit prices or productivity

factors  and wage rates. Labor unit prices are expressed as dollars per unit of the                                                                                                                    quantity being priced for example, dollars per square foot-and are subject to revision

due to change in the wage rate , fringe benefits and/ or tax  rates. Productivity, on the

other hand is expressed as man hours per unit and is constant over time for a given work task.

Labor cost calculated by entering the unit man-hours and the current wage rate without fringe benefits or labor taxes. The unit man-hours multiplied by the quantity to get the man-hours, which in turn multiplied by the wage rates, with the result being labor cost. Labor cost can then be divided by the quantity to get the unit labor cost, which can be used as a check against historical information.

An estimator should always calculate the unit labor cost and use it as a checking tool.

- Productivity

Productivity is the amount of time it takes a person to do a unit of work. Examples of productivity  factors  are man-hours per square foot of contact area for concrete forms or man-hours per ton of steel. They entered in the unit man-hour then multiplied by the quantity; the result is the man-hours needed to complete the line item.

- The cost of labor

Three basic elements that make up the cost of  labor are wages, fringe benefits, and payroll

taxes. Other elements that may be part of the cost are travel, per diem, ands over time. Projects performed by local contractors seldom need to account for travel and per Diem, and moist commercial projects tend not to require over time.

Of the three basic elements, two are negotiable, and one mandated by the government. Wages are paid based on hours worked with straight time generally being the first 8 hours worked per day up to 40 hours per week overtime comes generally in two multiples, time -and- a-half (wages *_I. 5) or double time(wages*2). All time over the base wage rate classified as premium time because it represents the premium cost of working a person beyond the agreed-upon normal pay period.

Fringe benefits are items such as a health and welfare, pension, and in some cases dental insurance and /or annuity. Benefits paid based on each hour worked and are not subject to the effects of premium time.

payroll taxes are government- mandated taxes and based on the amount of total paid. The combination of fringe benefits and payroll taxes commonly referred to as labor burden, this burden can vary widely from one trade to another, and the estimator can spend an inordinate amount of time calculating them for each crew

#### 5.4.1.2         Material Cost:

The cost or the price of the material affected many factors that include:

1. Quality affects price, because a higher quality usually means a higher price  4000 psi concrete is better than 3000 psi. so 4000psi is more strength and require more cement. so, a higher	is usually required for higher strength concrete).

2. Quantity affects price, because usually the larger the quantity purchased, the lower the price.

3.  Time often affects price in several ways, because it affects the production and delivery of a product. (E.g. if concrete is required at a certain time outside of normal business hours, the supplier may have to pay overtime rates to his employees and increase the price accordingly).

Some products are cheaper or more expensive at different times of the year, particularly if there is a seasonal demand, or if whether affects production or delivery. Time affects cost, because of changing markets, fluctuating supply and demand, inflation, and other economic factors.

4.  Place and location usually affects price through the means and distance of delivery and the accessibility of the site. Handling goods is costly, and changes in methods of delivery from factory to site affect the Final cost to the buyer. Freight costs are also determined by the type of goods and by the quantity delivered.

5.  The buyer affects the price at which he buys through his creditability as a customer, through the quantity he purchases, and by the marketing level at which he is able to purchase.

6.  The supplier affects the price because he, too, is a buyer as well as a seller of materials and services. Similarly, the relationship between a lesser and a lessee affect the rates at which plant and equipment rented

7.  Discounts List prices are usually not the prices at which goods sold, but are simply a datum, or price level, established as a basis for selling. Selling prices frequently quoted by percentage adjustments to list prices (which known as trade discounts)

8. Demand and supply of the material

#### 5.4.1.3           Equipment Costs:

A more complete title for this section should be "plant and equipment costs " to identify the two kinds”:

- Plant, which refers to those things that are "planted" in position, such as a
concrete-mixing plant.

- Equipment, which refers to those things that are mobile, such as a bulldozer.

The selection of the appropriate type and size of construction equipment often affects the required amount of time and effort and thus the job-site productivity of a project. It is therefore important for site managers and construction planners to be familiar with the characteristics of the major types of equipment most commonly used in construction.

factors that could affect the selection of excavators include:

- Size of the job: Larger volumes of excavation will require larger excavators, or smaller excavators in greater number.

- Activity time constraints: Shortage of time for excavation may force contractors to increase the size or numbers of equipment for activities related to excavation.

- Availability of equipment: Productivity of excavation activities will diminish if the equipment used to perform them is available but not the most adequate.

- Cost of transportation of equipment: This cost depends on the size of the job, the distance of transportation, and the means of transportation.

- Type of excavation: Principal types of excavation in building projects are cut and/or fill, excavation massive, and excavation for the elements of foundation. The most adequate equipment to perform one of these activities is not the most adequate to perform the others.

- Soil characteristics: The type and condition of the soil is important when choosing the most adequate equipment since each piece of equipment has different outputs for different soils. Moreover, one excavation pit could have different soils at different stratums.

- Weather and temperature: Rain, snow and severe temperature conditions affect the job-site productivity of labor and equipment.

5.4.2       Indirect Cost

Indirect costs consist of:

- Overhead Cost

- Profit

#### 5.4.2.1      Overhead cost:

These constriction costs of any kind that cannot attribute to any specific item of     work, if costs can attribute to an item of work, they should be and these costs will then come under one of these classifications already discussed, namely, material costs, labor costs, or equipment costs. Otherwise, they are over head costs.

Overhead costs can classify by applying an extension of the same reasoning by which we define overhead costs. That is, if costs can attribute to a specific job site because the costs arise only out of that particular Job, those costs are job overhead costs. If costs cannot attribute to any particular job, they are operating overhead costs. The scope and content of these two classifications vary with the conditions and requirements of the contract.

#### 5.4.2.2        Profit:

Profit is one of the primary motivations of all business, but it is not always the only one. Many small construction companies exit because the principal prefers to work at construction, and as long as he earns the living needs and expects he counts his business as a success.

An important aspect of profit is that it is one measure efficiency and success of accompany, but it is not always easy to apply. A "breakeven point" is reached when total income reaches total expenditure, and after that point further income is profit. But how is profit to be measured and expressed?

Profits = Total Income —Total Expenditures                                                ( Eq.1)

Usually added as a percentage to the total project cost. E. g . 12%

#### 5.5         Data Required for Preparing an Estimate:

In order to prepare a detailed estimate the estimator must have with him the following data:

1. Plans, sections and other relevant details of the work.

2. Specifications indicating the exact nature and class of materials to be used.

3. The rates at which the different items of work are carried out. 
To enable an estimator to take out the quantities accurately, the drawings must themselves be clear, true to the fact and scale, complete, and fully dimensioned. The estimator has also to bear in mind certain principles of taking out quantities.

#### 5.6         Steps in Preparation of an Estimate:

There are three clearly defined steps in the preparation of an estimate.

1 . Taking out quantities

In the first step of taking out quantities, the measurements are taken off from the drawings and entered on measurement sheet or dimension paper. The measurements to be taken out would depend upon the unit of measurement. For example, in the case of stone masonry in superstructure, length, thickness and height of the walls above plinth level would be taken out from the drawings and entered on the measurement sheet, whereas, in the case of plastering only the lengths and heights of the walls would be entered. Obviously, the unit of measurement in the first case is cubic meter and that in the second case is square meter.

2. Squaring out

The second step consists of working out volumes, areas, etc. and casting up their total in recognized units.

3. Abstracting

In the third step all the items along with the net results obtained in the second step are transferred from measurement sheets to specially ruled sheets having rate column ready for pricing.
The second and third steps above are known as working up. All calculations in these stages and every entry transferred should be checked by another person to ensure that no mathematical or copying error occurs.

Chapter 6

Work breakdown structure

6.1. Introduction:

A work breakdown structure is one form of project management forms; it is the basis for time estimation, resource allocation, cost estimation and collection. Company’s owners and project managers used to breakdown the large projects into smaller manageable projects that can be effectively estimated and supervised. However, the work breakdown structure is often misunderstood and not used as it should be in project management.

This chapter will illustrate the importance of WBS and discuss it from all points of view, although we need a large books to cover this object, we will try to introduce a comprehensive summery for work break down structure.

In this chapter you will find a definition for WBS in simpler form and then a world-wild definition, after that the chapter introduce a logical reasons to use WBS, in other words it answer the question “why to use WBS?” then the steps of making WBS and explain of each step. To make sure of understanding this object a sample example is then introduced and illustrated.

6.2. Definition of WBS:

Breakdown means to separate into simpler parts or to divide into parts and categories, structure is something arranged in a definite pattern of organization. Work break down structure then is the separation or decomposing of the project into smaller and simpler parts that can be easily managed and controlled.

These definitions imply that a work breakdown structure has the following characteristics:

- It is representative of work as an activity, and this work has a tangible result.

- It is arranged in a hierarchical structure.

- It has an objective or tangible result, which is referred to as a deliverable.

A WBS as defined in PMBOK guide-2000 edition is:

A deliverable-oriented grouping of project elements that organizes and defines the total work scope of the project. Each descending level represents an increasingly definition of the project work (Project Management Institute 2000)

6.3. Importance of breakdown structure:

There are many wild reasons to make a work breakdown structure for any project, some of them are:

- WBS provides a definition for the total scope of the work: WBS will give you the ability to set the scopes and to deliver a successful project.

- A well define work breakdown structure will give you, your team and your stakeholders a clear vision about what is needed to complete the project, and  provide an idea of how the work will be performed.

- Ensure that work elements are related to only one work effort.

- It helps to assign the responsibilities: by work breakdown structures you can give each person in your team his work and make him know what he should do.

- To get accurate estimation of cost, risk and time. As you breakdown your project you can make do with each aspect as a discrete project; this will make it easier to calculate it’s cost and time needed to do it, the total cost of the project is then the sum of all its aspects cost. And by calculating the time needed for each “smaller project” and using scheduling you can determine the total time needed.

- WBS is excellent to communication and creates a basis for understanding between you and your team and your stakeholder.

- WBS gives you the possibility to breakdown activities into smaller pieces, this will make it easier to manage the work and follow up with all activities.

- WBS is the foundation in managing process which affecting other managing process like estimation and risk management.

6.4. Factors affecting WBS:

WBS depend on several factors, some of them are:

- Size and complexity of the work.

- Project manager judgment of work.

- Time available to complete the project.

- Degree of uncertainty and risk involved.

6.5. Steps to make WBS:

- Specify the project objective and what the final product of this project is.

- Determine the main phases of your project and put them in the first level: the phase is the major component of the project life cycle. For example if you want to write a book; this will be the same as put the outline of this book.

- Take each of these phases and break it down to its components; this process will continued until reaching a separated activities that cannot broken down any more, these levels are the second level of WBS. Each element here is called WBS entry.

- The last level in WBS is the activities which cannot be broken down. Activities are where deliverables are assigned to an individual; each activity is performing a work process during the project life.

- After doing above it is the time of validation check using bottom-up approach: a bottom-up validation works like this:

- [For each WBS entry that decomposes into activities; ask yourself the question “if I had all the deliverables from each of these activities. Would my WBS entry deliverable be completed?”if the answer is yes, move to the next WBS entry. If the answer is no, add in the missing activities.

- Once the evaluation of the lowest level WBS entries and activities is complete, examine the next higher level of WBS entries. For each phase ask “if I had the deliverables from the WBS entries that are part of this phase, would the phase deliverable be complete?” if the answer is yes, move on to the next one, if the answer is no then add in the missing WBS entries.]       Kim Colenso, Managing Principal, Artemis Management Systems

- Compare the currently WBS deliveries with the original objective of the project, if it is not then there still a work to do.

6.6. Example of WBS:

| Phase 1 – WBS Level 1 | 1.0 Requirements Phase |
| --- | --- |
| WBS Entry - WBS Level 2 | 1.1 Business Objectives |
| Activity – WBS Level 3 | 1.1.1 Create Draft Objectives |
| Activity – WBS Level 3 | 1.1.2 Review Draft Objectives |
| Activity – WBS Level 3 | 1.1.3 Update Objectives |
| Activity – WBS Level 3 | 1.1.4 Approve Objectives |
| Milestone – WBS Level3 | 1.1.5 Business Objectives Complete |
| WBS Entry – WBS Level 2 | 1.2 Draft Requirements |
| Activity – WBS Level 3 | 1.2.1 Interview Stakeholders |
| Activity – WBS Level 3 | 1.2.2 Write Draft Requirements |
| Activity – WBS Level 3 | 1.2.3 … |
| WBS Entry - Level 2 | 1.3 Final Requirements |

…

Phase 2 – WBS Level 1 2.0 Design Phase

…

Phase 3 – WBS Level 1 3.0 Development Phase

…

Phase 4 – WBS Level 1 4.0 Test Phase

…

In this example we can see the main components of the WBS: first of all the example is divided into main ideas or man aspects, this is represented by phases and is named as level 1.

Each phase then is broken down into other pieces which is the entry of WBS as named as level2.

The entries are then divided into activities which has level number 3. Each group of activities “level 3” is grouped to make entry “level 3” and then the entries “level 2” is grouped to make phase “level 1” all phases then represent the whole project.

Discussion:

As mensioned previously it is clear that the WBS is very important in project management, this because it is simplify the work complex work and put all activities under control, and because it perform a foundation for other project management aspects like cost estimation,  using WBS will save time money, time and efforts. There is no doubt that WBS is a main pillar of any project management, and is the leader for success for any manager.

Summary”

Work breakdown structure is one form of project management forms, it is defined as the simplifying of complex projects into simpler form by breaking it down into smaller chunks. The reasons over using WBS is to go over all works during the project life cycle and to make managing process simpler which will lead to save time, cost and efforts and finally to success in project management.

To make a WBS for any structure, the main scopes are determined taking into consideration the final product we need then the project is broken down into its main components then each of these is also broken down… this process is continued until reaching at last the activities which cannot be broken down any more.

Once we attend the WBS we move to next step of project management and prepare it, finally, all project management aspects are collected to give a successful management for any project

Chapter 7:

Risk analysis and management

7.1 Overview

Risk is an entity that appears in all aspects of projects. Therefore, to reach the project success we require managing risks related to our projects. The need for project risk management has been widely recognized. The purpose of project risk management is to improve project performance by systematically identifying and assessing risks, developing strategies to reduce or avoid them and maximizing opportunities. The science of risk management was developed back in the sixteenth century during the Renaissance, a period of discovery, but regarding the subject of Risk Management Process (RMP), since 1990 a large number of RMPs have been generated to address the need for more effective risk management.

A conventional Risk Management Process (RMP) contains two main phases, (a): risk assessment that includes risk identification and risk analysis, and (b): risk response that is deciding what, if anything should be done about the analysed risks.

7.2.  Introduction:

A risk is something that may happen and if it does, will have a positive or negative impact on the project. A few points here "That may happen" implies a probability of less then 100%. If it has a probability of 100% - in other words it will happen - it is an issue. An issue is managed differently to a risk. A risk must also have a probability something above 0%. It must be a chance to happen or it is not a risk.

The second thing to consider from the definition is "will have a positive or negative impact". Most people dive into the negative risks but what if something goes right?

The benefits of risk management in projects are huge. One can gain a lot of money if deal with uncertain project events in a proactive manner. The result will be minimizing the impact of project threats and seize the opportunities that occur. This allows delivering a project on time, on budget and with the quality results demanded. Also team members will be much happier if they do not enter a "fire fighting" mode needed to repair the failures that could have been prevented.

The broad objectives of the project risk management process are to:

- enhance the capability of the organization;

- extend the organization’s overall risk management processes to projects, and apply them in a consistent way; and

- enhance the management of projects across the organization and obtain better project outcomes, in terms of schedule, cost and operations performance, by reducing risks and capturing opportunities.

Good project risk management within an organization has the following characteristics:

- project risk management activities commence at the initiation of the project, risk management plans are developed and risk management continues throughout the project life cycle;

- project risk management is not a discrete stand-alone process, but is integrated with other project management functions; and

- the implementation of project risk management is the responsibility of all project stakeholders and they participate actively in the process.

7.3  Project risk management Process:

The objective of risk management is to identify and manage significant risks. It involves several key phases, with feedback through a monitoring and review process. In most projects, risk management overlaps with other management processes and procedures, in that many of the steps are undertaken as part of normal project management. This provides the basis for integrating risk management and project management activities.

Steps of Project risk management Process:

1. Establish the context:

Establishing the context is concerned with developing a structure for the risk identification and assessment tasks to follow. This step:

- establishes the organizational and project environment in which the risk assessment is taking place;

- specifies the main objectives and outcomes required;

- identifies a set of success criteria against which the consequences of identified risks can be measured; and

- Defines a set of key elements for structuring the risk identification and assessment process.

Context inputs include key project documents, such as the project execution strategy, project charter, cost and schedule assumptions, scope definitions, engineering designs and studies, economic analyses, and any other relevant documentation about the project and its purpose.

The output from this stage is a concise statement of the project objectives and specific criteria for success, the objectives and scope for the risk assessment itself, and a set of key elements for structuring the risk identification process in the next stage.

2. Identify the risks

Risk identification determines what might happen that could affect the objectives of the project, and how those things might happen. The risk identification process must be comprehensive, as risks that have not been identified cannot be assessed, and their emergence at a later time may threaten the success of the project and cause unpleasant surprises. The process should be structured using the key elements to examine risks systematically, in each area of the project to be addressed.

A number of techniques can be used for risk identification, but brainstorming is a preferred method because of its flexibility and capability, when appropriately structured, of generating a wide and diverse range of risks. Information used in the risk identification process may include historical data, theoretical analysis, empirical data and analysis, informed opinions of the project team and other experts, and the concerns of stakeholders. The output is a comprehensive list of possible risks to the successful outcome of the project, usually in the form of a risk register, with management responsibilities (risk owners) allocated to them.

Threats may be:

- Human:  from individuals or organizations, illness, death, etc.

- Operational: from disruption to supplies and operations, loss of access to essential assets, failures in distribution, etc.

- Reputation: from loss of business partner or employee confidence, or damage to reputation in the market.

- Procedural: from failures of accountability, internal systems and controls, organization, fraud, etc.

- Project: risks of cost over-runs, jobs taking too long, of insufficient product or service quality, etc.

- Financial: from business failure, stock market, interest rates, unemployment, etc.

- Technical: from advances in technology, technical failure, etc.

- Natural:  threats from weather, natural disaster, accident, disease, etc.

- Political - from changes in tax regimes, public opinion, government policy, foreign influence, etc.

3. Analyze and evaluate the risks

Risk assessment is the overall process of risk analysis and risk evaluation. Its purpose is to develop agreed priorities for the identified risks.

- Risk analysis is the systematic use of available information to determine how often specified events may occur and the magnitude of their consequences.

- Risk evaluation is the process of comparing the estimated risk against given risk criteria to determine the significance of the risk.

[

The assessment process:

- determines the consequences of each risk, should it arise;

- assesses the likelihood of those consequences occurring;

- converts the consequence and likelihood ratings to an initial priority for the risk; and develops agreed risk priorities and inherent risk levels.

The agreed priorities are used to determine where the greatest effort should be focused in treating identified risks. They facilitate structured action planning and resource allocation. This stage of the risk management process generates a prioritized list of risks and a detailed understanding of their impacts upon the success of the project should they occur. The consequence and likelihood ratings and the agreed risk priorities are all recorded in the risk register.

4. Treat the risks

The purpose of risk treatment is to determine what will be done in response to the risks that have been identified, in order to reduce the overall risk exposure. Unless action is taken, the risk identification and assessment process has been wasted. Risk treatment converts the earlier analyses into substantive actions to reduce risks.

There are four things you can do about a risk. The strategies are:

- Avoid the risk. Do something to remove it. Use another supplier for example.

- Transfer the risk. Make someone else responsible. Perhaps a Vendor can be made responsible for a particularly risky part of the project.

- Mitigate the risk. Take actions to lessen the impact or chance of the risk occurring. If the risk relates to availability of resources, draw up an agreement and get sign-off for the resource to be available.

- Accept the risk. The risk might be so small the effort to do anything is not worth while.

The primary inputs to this step are the lists of risks and their agreed priorities from the previous step and the current project plans and budgets.

Risk treatment involves:

- identifying the options for reducing the likelihood or consequences of each Extreme, High or Medium risk;

- determining the potential benefits and costs of the options;

- selecting the best options for the project; and

- developing and implementing detailed Risk Action Plans.

Once you have worked out the value of risks you face, you can start to look at ways of managing them. When you are doing this, it is important to choose cost effective approaches - in most cases, there is no point in spending more to eliminating a risk than the cost of the event if it occurs. Often, it may be better to accept the risk than to use excessive resources to eliminate it.

Risk may be managed in a number of ways:

- By using existing assets:  Here existing resources can be used to counter risk. This may involve improvements to existing methods and systems, changes in responsibilities, improvements to accountability and internal controls, etc.

- By contingency planning: You may decide to accept a risk, but choose to develop a plan to minimize its effects if it happens. A good contingency plan will allow you to take action immediately, with the minimum of project control if you find yourself in a crisis management situation. Contingency plans also form a key part of Business Continuity Planning (BCP) or Business Continuity management (BCM).

- By investing in new resources: Your risk analysis should give you the basis for deciding whether to bring in additional resources to counter the risk. This can also include insuring the risk: Here you pay someone else to carry part of the risk - this is particularly important where the risk is so great as to threaten your or your organization's solvency.

5. Monitor and review:

Continuous monitoring and review of risks ensures new risks are detected and managed, and that action plans are implemented and progressed effectively. Review processes are often implemented as part of the regular management meeting cycle, supplemented by major reviews at significant project phases and milestones.

Monitoring and review activities link risk management to other management processes.

They also facilitate better risk management and continuous improvement.

The main input to this step is the risk watch list of the major risks that have been identified for risk treatment action. The outcomes are in the form of revisions to the risk register, and a list of new action items for risk treatment.

6. Communicate and consult:

Communication and consultation with project stakeholders may be a critical factor in undertaking good risk management and achieving project outcomes that are broadly accepted. They help owners, clients and end users understand the risks and trade-offs that must be made in a large project. This ensures all parties are fully informed, and thus avoids unpleasant surprises. Within the project management team, they help maintain the consistency and ‘reasonableness’ of risk assessments and their underlying assumptions.

In practice, regular reporting is an important component of communication. Managers report on the current status of risks and risk management as required by sponsors and company policy. Senior managers need to understand the risks they face, and risk reports provide a complement to other management reports in developing this understanding.

The risk register and the supporting action plans provide the basis for most risk reporting.

Reports provide a summary of project risks, the status of treatment actions and an indication of trends in the incidence of risks. They are usually submitted on a regular basis or as required, as part of standard management reporting. Major projects may require more extensive reporting on a periodic basis or at key milestones.

7.4.  When to use Project Risk Management:

Normally business changes are made in order to change a level of activity in some way, whether it is sales, cash flow, productivity, or product portfolio. When attempts are made to make such changes, too often the business reverts to the old levels of activity as soon as management attention is diverted.

Fig.7.1: Changing levels of activity

To make lasting changes, the change is best managed as a project. The diagram illustrates a properly managed project leading to a lasting change in levels of activity. If the project does not meet the requirements of the business the line will tend to revert to the previous level of activity over time.

Money invested in reducing risk in the early stages of a project is money well invested. Any risks incurred during the project have to be diagnosed, and fixed. Also things have already gone wrong by the time the problem is detected and this will add to the costs. The diagram (Fig.8) illustrates the way costs of correcting risks at the initial start up phase of a project balance against costs of correcting and managing a failure. The rate of increase in cost of risk is exponential, and any risks that can be reduced or eliminated during the start up phase will pay a generous dividend in limiting the total project cost. It is much better to reduce the risks at the start up phase of the project than to allow a contingency on a basis that things are bound to go wrong.

Fig.7.2: Cost of fixing risks in projects

### What if I have already begun my project?

### This is not a problem. You can perform a risk assessment on the project and begin to apply project risk management at any time. The risk assessment should find some of the major things which are about to go wrong, and identify potential failures as the project continues.

7.5 Planning a Risk Assessment

Risk Assessment in a project is the most difficult phase of all to carry out. From the definition a risk is a combination of uncertainty and constraint. Constraints are usually difficult to remove, though they are important to understand. For instance, a constraint that the project must be finished in time to reflect a new piece of legislation is easy to understand. Manpower constraints are often more uncertain, such as the availability of skilled staff at the critical phase of the project. But as mentioned a constraint could be defined as an uncertainty.

This just goes to prove how clear the thinking has to be if Risk Assessment is to succeed. So let's try to be absolutely clear what we mean by uncertainty and constraint. Certainty defined as 'Undoubted fact, indubitable prospect, thing in absolute possession, beyond possibility of doubt.' Since the essence of project management is estimation, this tells that just about everything in the project is uncertain. The constraint defined as 'compulsion, confinement'. So in the process of Risk Assessment we are going to attempt to select those areas of the project with the most severe constraints and the highest uncertainty.

Not least among the areas of uncertainty are the internal politics of the project. Some people will want to look good to their bosses, or will want to have a quiet life, or for some other reason may wish to conceal the weaknesses in their project plans. It may be that a sub project manager will be able to move on before the delivery date of his module, so it is in his interests to keep the thing going rather than suffer the agonies of trying to get the project back on track. Or the project may have developed a 'completion culture', where all problems are ignored in order to deliver on time, even though an impartial observer can see that the project is not going to meet its requirements.

The three circles indicate the most important quality measurements of the project. And the most important of these is meeting the users' requirements. How many projects do we know where the team has not bothered with ensuring that the users understand what is proposed, but has got on with the interesting part of the project - actually implementing it

Fig.7.3: Elements of project success

Finding out and understanding the users’ requirements, building the project schedules, and preparing the project financial plan, are all an essential part of preparing for the project. These activities should all be carried out in the first phase of the project.

If you have a detailed project plan, statement of user requirements, and budget, then think of the three legged stool - if all three legs are not the same length the stool will topple. These three documents are the three legs of your project plan. So make absolutely certain that they are consistent.

After that, all that you have to do to complete your Risk Assessment is to explore each task in the project plan and seek uncertainty. It is essential to be absolutely clear in your thinking. For instance, 'The project will be late.' is not a Risk, it is an Effect. You need to consider what the things are that could make each TASK in the Project Plan late.

7.6.  Conclusion:

Risk management is not a complex task. If you follow the risk management process steps, you can put together a risk management plan for a project in a short space of time. Without a plan, the success of the project, and your reputation as a Project Manager, are on the line. Follow the following rules of and you will increase your chances of success:

Rule 1: Make Risk Management Part of Your Project

Rule 2: Identify Risks Early in Your Project

Rule 3: Communicate About Risks

Rule 4: Consider Both Threats and Opportunities

Rule 5: Clarify Ownership Issues

Rule 6: Prioritize Risks

Rule 7: Analyze Risks

Rule 8: Plan and Implement Risk Responses

Rule 9: Register Project Risks

Rule 10: Track Risks and Associated Tasks

Chapter 8

Quality management

8.1. Introduction:

In all production process, there is a need to monitor the extent of the product with a determined standards and specifications. In general, managers know that the two main interrupters for the production process is the deviation of the product from standards, and the excessive variability around target specifications. Control management aims to go over these main problems and put the suitable solution to solve them.

In general, control management is divided into three main aspects; quality planning, quality assurance and quality control. The start is with planning which include as will be explained the determination of goals, resources,… etc. then during the production process the quality assurance is applied to make sure that the product is applied, finally after the product is ready quality control is made which include several checks to insure that the specification is achieved.

8.2. Quality planning:

Every project should have a quality planning, although in reality, very few do it. According to ISO9000.2000 the definition of the quality planning is “art of quality management focus on sitting quality objective and specifying necessary operational processes and related resources to fulfill quality objective.”

Quality planning can also be defined as the systematic process by which the standards and specification of a product is identified and to determine suitable ways to satisfy theses standards in order to achieve quality in the product being improved. Quality planning translates quality policy into measurable objectives and requirements.

Quality planning helps to identify the goals of the project to insure that the final product will meet the needs of customer, it is very essential if the company want to provide the customer with confidences that it will give them a perfect product, and that it will find a solution for any problem in the manner satisfying their needs.

Quality planning define the steps that will be carried to execute the product or service, it states everything you are going to do, to insure the quality of your final product. The first step in planning is to define the goals of your project; second step is to set out quality assurance plan, next is to define quality control plan. In this manner a control management for the project has been achieved which will give the customer a highly confidence that the project will succeed.

8.2.1. Quality planning inputs:

The inputs to quality planning are:

- Enterprise environmental factor: it is all the internal and external organizational factors that influence the project success, the objective of inputting it in the planning is to assure that the plan is cognizant of the bigger picture.

- Organizational process assets: it is any process –related assets that may influence the project outcome, Assets commonly include informal or formal quality policies, guidelines, and procedures, as well as historical databases related to quality.

- Project scope statement: it describes the major deliverables, acceptance criteria, objectives, assumptions, constraints, and a statement of the work for the project, The Project Scope Statement provides a basis for making future project decisions. Project Managers commonly plan project activities so that the project deliverables meet the desired level of quality.

[

- Project Management Plan: The Project Management Plan defines how the project is expected to behave through the executing, monitoring and controlling, and closing process groups. In addition, it specifies that a quality plan and philosophy will be adopted, and it refers to other quality procedures that may be relevant. The Project Management Plan details the completed project work to be inspected and verified.

8.3. Quality assurance:

quality assurance is the systematic process or processes of checking made to ensure the product or service under development (before the work is completed) will meets the specific requirements

The most popular steps to perform quality assurance is Shewart cycle which developed by Dr. W. Edwards Deming. This cycle for quality assurance is consists of for steps: plan, do, check and act. These steps are commonly abbreviated as PDCA. We can summarize these steps as follow:

- Plane: establish and define the objective and processes to establish the new product.

- Do: implement the process developed.

- Check: to check the results and compare it with the defined objectives.

- Act: if the results required to be changed, improvement action should be applied.

The goal of PDCA is to insure the excellence in all methods of developing the product or service. PDCA is an effective method for maintain the quality assurance, this because it analyze all the circumstances and methods that used to improve the product or service. The repeated use of PDCA through the life time of developing the product helps in increasing the company efficiency. It also helps to determine whether the steps used to develop the product is within time and condition needed.

Quality assurance need a degree of details to be fully and successfully applied, for example planning may include an investigation into the raw materials that will be used in manufacturing, check could include the customer feedback to insure that the product meets customer needs, acting could mean the total revision of manufacturing process in order to correct any existing flaw.

ISO9000: it is an international specification that used by companies to ensure that their quality assurance is in place and effective.

8.3.1 Quality assurance engineer:

The goal of QA engineer is to try and make the product or service not work properly or not to meet specifications, so that the developer can catch errors before happened, QA professionals should have variety of background, they are free thinkers who like puzzles. Every company produce a product needs a QA engineer who should have special skills such as understanding user behavior and to have the ability to expect errors in product developing, this of course behind his specialization in the product field (chemical, industrial, mechanical,…etc).

8.4. Quality control:

Quality control is the heart of industrial manufacturing. Quality control is similar but not the same as quality assurance, [“Quality is meeting or exceeding customer expectations at a cost that represents a value to them."  H. James Harrington]. Quality control is the process applied to maintain a certain quality for a given product or service according to determent specifications, in other words, quality control designed to ensure continues production of product with specific quality to certain standard.  Quality control (QC) and quality assurance (QA) are sometimes expressed together in one process (QA\QC).

Essentially the quality control includes the examination of the product. In any company, the job of quality control team is to identify the product that does not meet the standard of the company, once it identified the team search what the problem is, and then they determine whether to stop producing it or improve the production process to get at least the lowest level of quality needed.

8.4.1. Importance of quality control:

in general, the quality of any product increase its value, and give it a trade name which will reflect into customer satisfaction, also it insure that all the pieces of the same product are of the same quality, which will provide a certain characteristic of this product which will be defined in customer daily life, this will result in perfect marketing of this product.

8.4.2. Quality control process:

Quality control process is start by determine the standard and specification that the product must meet, then the extend of the quality control action is determined (for example determine the fraction of units to be tested), after the units are product the real world data are collected and studied (for example, the fraction of units that failed) after that the results should be reported to the manager.

After that the correction process is started, and a decision should be taken about what to do (for example; reject the produced unites or repair it). If too many number of units failed or poor service occurs, a plane should be devised to improve the quality of that product or service, and then this plane must be put into action.

Finally, the quality control process should be continued to make sure that the product our plane will give the product that meet the specification, and to solve any problem if happened during production process.

8.4.3. The test plane:

For quality control to be effective, you must test the same things at the same manner every time, when you change your test your result become inconsistent. You need a test plan.

A test plan is simply a high-level summary of the areas you will test, how many times you repeat the test and at which stage of development or production process you will make your test, a test plan also needs an estimate of the duration of testing, and statement of any required resources.

To help define what we should test, we can do this:

- Determine why we do make this product, and what the purpose of the product is.

- Determine the business goals, if any, behind this product.

- Determine the audience for this product and if they well get benefits of the product.

- Determine the tips of works that well be made upon the product to be effective

Once the entire above are determined equality control manager can decides what needs to be tested, and then developed his test plan.

8.5. Some issues to consider:

The goals that are set to the product will have a great deal to do with the kind of production being improved.

Quality control can be difficult when you find your resources limited or overextended. Manager will often find it impossible to set everything or to verify everything. Some consistent test cases must be developed then to check the major problem areas.

Testing and creating test cases is always a learning experience. As the manager test and refine his test cases he will find a balance between not enough testing and just plain overkill, and between extremely detailed test cases and simple spot checks.

Finally we can see that the quality control process has the major shortcoming of being reactive to problem. Quality control sets the standards for product and test for its component that fall below the standards, where areas quality assurance improves the invention process of the product i.e. during the work.

PART TWO

APPLICATION OF CONSTRUCTION MANAGEMENT

((Al-Jadera Basic School))

Page

1-  Graduation project part two description

2-   Project description.                                                                                 	66

3 - Work Breakdown Structure(WBS).                                                                  68

4 – Quantity surveying.                                                                                            68

5 - Activities List and coding.                                                                                   68

6. Activity duration and productivity	69

7 - Bill of quantity (BOQ) preparation; quantities, cost, resources,

and man hours.                          	69

8 – Project price .                                                    	70

9- Project network.                                                        	70

10 –Project budgeted.                                                                                              70

11 –Project duration.                                                                                              70

12-  Result & Conclusion

PART TWO:

Application Of Construction Management ..

Al-Jadera Basic School

1-  Graduation project part two description

This part applies the theoretical part at an a real project which is Al-Jadera Basic School, by putting the WBS to the project, quantity surveying; estimating and manages resources, according to the drawings and specifications.

At this part, managing is done using computer software’s programs which are; Primavera software; this program is used for schedule and the durations of the project.

WBS Chart Pro, And Microsoft Excel.

According to the drawings and specifications, a specific method is used in managing this project, by following these steps:

- WBS Preparation.

- Quantity Surveying.

- Activity list & activity coding.

- Bill of quantity (BOQ) preparation; quantities, cost, resources, and man hours.

- Activity durations & productivity.

- Project price.

- Project network.

- Project budgeting.

- Project duration.

2.  Project Description:

Al-jadera basic school is allocated  in Al-jadera village near Ramallah , it accommodated  large number of students because of its huge area , so it is considered the biggest school in Ramallah area.

It achieves all student services and structural needs , it consists of 4 floors which contain several student classrooms, staff  room, principle room, secretary room, kitchen, canteen, students and staffs bathrooms, (computer, technology, science, and chemistry) labs, stores, prepare room, main hall, library, and sports room.

The areas of the floors are different, and it’s summarized as follow:

| Areas Summary |  |
| --- | --- |
| Ground Floor | 635.36 m2 |
| First Floor | 619.18 m2 |
| Second Floor | 619.18 m2 |
| Third Floor | 304.46 m2 |
| SUM | 2178.18 m2 |

Table 1 : Areas Summary.

The following Picture shows the site plan:

Figure 1 : Site Plan.

3.  Work Breakdown Structure (WBS):

The suitable WBS selected according to the drawings and specifications, to divide the project into packages, which makes managing the project easy and controlled well, WBS allows limiting the price of each package in the project, the WBS of the project is divided into these levels:

Level One:  The whole of the project.

Level Two: The earth works, the floors, landscape and infra structure of the project

Level Three: The types of work (structural, electrical, mechanical, architectural).

Level Four:   The work packages of types in level three.

Level Five:   The Activities.

The project WBS is shown in Appendix A

4.  Quantity Surveying :

We accomplished the  calculations according to the scientific rules and  specification with considering adequate details in order to determine the total material cost of project and quantity for each activity . The project Quantity surveying is shown in Appendix B

5. Activity List & Coding:

The lowest level of the WBS is composed of work packages, and these are broken down into the specific activities that are included on the activity list.

The Activity List is the complete list of the scheduled activities for a project. As it is used to help develop the project schedule and estimate needed resources, it serves as an input to the following processes: sequence activities, estimate activity resources, estimate activity durations, and develop schedule.

Activities are prepared according to the method of work, and through the work breakdown structure, and a particular encoding used to represent each activity; this makes easy access for each activity in the network of the project.

The activity code used at this project can be illustrated as follows:

- The first letter: represents the 1st letter at level two in the WBS, like;

0:  Ground floor

1:  First floor

2:  Second floor

3:  Third floor

- The second letter: represents the 1st letter at level three in the WBS, like;

E:  Earth work

C:  civil work

M:  Mechanical work

L :  Electrical work

A:  Architecture work

I: Infra structure

S: Land scape

- The third letter: represents the 1st letter at level four in the WBS, like;

W: walls & columns.

RS: roof slab &stairs.

And so…

For example; activity (F1CW) is located at 1st floor, civil works, walls & columns. The project activity list & coding is shown in Appendix C.

6. Activity durations & productivity.

We done statistical surveying work and determine the productivity rate for each activity then we determine the duration for it by using the following equation

Duration = (Quantity /(NO of crew*productivity ))

For example : the activity of  Tile for Ground floor

Quantity =503.92 m2

Productivity = 20 m2 /day /crew                  ,   crew (1 Skilled + 1 Unskilled )

NO of crew = 3

Duration = (503.92 /(20*3)) = 9 day

7.  Bill of quantity (BOQ) preparation; quantities, cost, resources, and man hours.

After doing the activity list and quantity works , we did a study to determine the resources of each activity and the cost of these resources in order to determine the cost of activities

As in the previous example:

Cost of 1m2 of tile = 60 NIS

Total man hours = 9 *3 *16 = 432 hr

Cost of one crew = 260 NIS/day

Total  cost of labor = 260 *9 *3 = 7020 NIS

Cost  of I m2 =60 NIS

Total cost of material = 503.92 *60 =30235.2 NIS

Total cost of activity = 7020 + 30235.2 = 37255.2 NIS

The Bill of quantity (BOQ) preparation; quantities, cost, resources, and man hours is shown in Appendix D.

8 .Project Price :

Is the price which is used for BIDS which includes ( direct cost, indirect cost and profit). The  direct cost was calculated in the previous step ( step 6 ) .For indirect cost we determine the items that falls under it .By doing the analysis of direct and indirect cost including the risk and profit we determine the factor that we need to convert from cost to price. The project price is shown in appendix E.

9. Project Network :

By considering the physical constrains we determined the relationships between construction activities using finish to start relationship (FS). The project network is shown in Appendix F.

10. Project Budgeted :

In  Appendix G we attached two tables one for the total Budgeted cost and the other for the total price.

11. Project duration :

After determining the duration for each activity and the relationships between activities ,the total project duration is determine as shown in Appendix H . beside of the activities and its duration we attached the bar chart and the total resource profile and resource profile for each individual crew .

References:

- Chapman, C. and Ward, S. (2003). Project Risk Management, John Wiley & Sons, Chichester, England

- Lichtenberg, S. (2000). Proactive management of uncertainty using the successive principle: a practical way to manage opportunities and risks, Polyteknisk Press, Lyngby, Denmark.

- http://www.acet.or.tz/gama/Risk_management.htm

- http://www.projectsmart.co.uk/10-golden-rules-of-project-risk-management.html

- http://www.pmis.co.uk/project_risk_management.htm

- كتاب صالح مبارك للاداره الهندسيه

- Process planning and cost estimation for "Kesavan  R, Elanchezhian"

- Cost estimating 2nd edition Rodney D, Stewart

- CPM in construction management 5th edition James J . O'Brain

- Quality Management Hanzer